## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a data engineer, I want to collect and clean Azure usage data so that it becomes ready for demand forecasting. | MUST HAVE | Dataset availability | Backend | 3- Completed
Sprint 2 | Sprint 2 | US002 | As a data scientist, I want to engineer demand-driving features such as seasonality indicators, lag variables, and usage trends so that the dataset becomes suitable for machine learning models. | MUST HAVE | Cleaned dataset | Backend | 3- Completed
Sprint 3 | Sprint 3 | US003 | As a data scientist, I want to train ARIMA and XGBoost models using the cleaned data so that I can compare their forecasting accuracy. | MUST HAVE | Feature engineered dataset | Backend | 3- Completed
Sprint 3 | Sprint 3 | US004 | As a data scientist, I want to evaluate model performance using metrics like MAE and RMSE so that the best forecasting model can be selected. | MUST HAVE | Trained Model | Backend | 3- Completed
Sprint 4 | Sprint 4 | US005 | As a developer, I want to deploy the forecasting model so that Azure demand predictions can be generated automatically. | SHOULD HAVE | Selected model | Backend | 1- Not Started
Sprint 4 | Sprint 4 | US006 | As a developer, I want to integrate the predictions into a dashboard so that the Azure supply team can monitor demand trends. | COULD HAVE | Deployed model | Frontend | 1- Not Started
Note on F1: ====== ID#AAAB05tlyP4 Sumeet Kumar Barua08 (2026-03-09 15:19:09) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US001 | T1 | Collect Azure service usage dataset with regional and timestamp information for demand forecasting | 2026-02-06 | 2026-02-08 | Backend | Data Collection | 3- Completed | 5 | Day 1: TRUE; Day 2: TRUE; Day 3: TRUE
US001 | T2 | Clean and validate dataset by handling missing values, removing duplicates and standardized formats | 2026-02-09 | 2026-02-12 | Backend | Data Cleaning & Validation | 3- Completed | 4 | Day 2: TRUE; Day 3: TRUE; Day 4: TRUE; Day 5: TRUE
US002 | T3 | Integrate external variables such as economic trends, market demand trends | 2026-02-20 | 2026-02-23 | Backend | Feature Engineering | 3- Completed | 4 | Day 3: TRUE; Day 4: TRUE; Day 5: TRUE; Day 6: TRUE
US002 | T4 | Create lag variables and seasonality indicators for time series forecasting | 2026-02-24 | 2026-02-27 | Backend | Feature Engineering | 3- Completed | 4 | Day 4: TRUE; Day 5: TRUE; Day 6: TRUE; Day 7: TRUE
US003 | T5 | Train ARIMA model using historical Azure usage data | 2026-03-05 | 2026-03-07 | Backend | Model Training | 3- Completed | 8 | Day 5: TRUE; Day 6: TRUE; Day 7: TRUE
US003 | T6 | Train XGBoost model for demand forecasting | 2026-03-08 | 2026-03-10 | Backend | Model Training | 3- Completed | 8 | Day 6: TRUE; Day 7: TRUE; Day 8: TRUE
US004 | T7 | Evaluate models using MAE and RMSE to compare performance | 2026-03-11 | 2026-03-13 | Backend | Model Evaluation | 3- Completed | 4 | Day 7: TRUE; Day 8: TRUE; Day 9: TRUE
US004 | T8 | Select best performing model for forecasting | 2026-03-14 | 2026-03-15 | Backend | Model Selection | 3- Completed | 3 | Day 8: TRUE; Day 9: TRUE
US005 | T9 | Deploy forecasting model for demand prediction pipeline | 2026-03-20 | 2026-03-24 | Backend | Model Deployment | 1- Not Started | 4 | Day 9: TRUE; Day 10: TRUE; Day 11: TRUE; Day 12: TRUE; Day 13: TRUE
US006 | T10 | Integrate predictions into visualization dashboard | 2026-03-25 | 2026-03-29 | Frontend | Dashboard Integration | 1- Not Started | 10 | Day 10: TRUE; Day 11: TRUE; Day 12: TRUE; Day 13: TRUE; Day 14: TRUE
Note on D2: ====== ID#AAAB05tlyPg Please enter the dates in either of these formats (2026-03-09 15:19:09) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAAB05tlyPs Please enter the dates in either of these formats (2026-03-09 15:19:09) 9/15/2016 or 15-Sep-2016
Note on K3: ====== ID#AAAB05tlyPE Sumeet Kumar Barua08 (2026-03-09 15:19:09) Pending effort hours after completion of day 2 work
Note on M3: ====== ID#AAAB05tlyPQ Sumeet Kumar Barua08 (2026-03-09 15:19:09) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAAB05tlyQE Sumeet Kumar Barua08 (2026-03-09 15:19:09) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAAB05tlyPI Sumeet Kumar Barua08 (2026-03-09 15:19:09) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAAB05tlyPc Sumeet Kumar Barua08 (2026-03-09 15:19:09) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAAB05tlyP8 Sumeet Kumar Barua08 (2026-03-09 15:19:09) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAAB05tlyP0 Sumeet Kumar Barua08 (2026-03-09 15:19:09) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAAB05tlyPU Sumeet Kumar Barua08 (2026-03-09 15:19:09) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAAB05tlyQA Sumeet Kumar Barua08 (2026-03-09 15:19:09) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAAB05tlyPo Sumeet Kumar Barua08 (2026-03-09 15:19:09) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAAB05tlyPY Sumeet Kumar Barua08 (2026-03-09 15:19:09) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAAB05tlyPM Sumeet Kumar Barua08 (2026-03-09 15:19:09) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Missing values and inconsistent records in dataset | Cleaned dataset, removed duplicates and standardized column formats
Sprint 2 | Day 1 | Identifying important features influencing resource demand | Analyzed dataset and selected operational and economic indicators
Sprint 2 | Day 3 | Difficulty capturing temporal demand patterns | Created lag variables, rolling statistics, and seasonality features
Sprint 3 | Day 2 | Understanding suitable forecasting models for demand prediction | Studied ARIMA and XGBoost models and their applicability
Sprint 3 | Day 4 | Handling categorical data and model training errors | Encoded categorical variables and successfully trained models
Sprint 4 | Day 2 | Difficulty integrating forecasting outputs with capacity planning workflow | Standardized prediction output format and connected model results to planning dashboard

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-02 | 16-02-2026 | Backend | Document dataset structure and preprocessing steps clearly | Ignoring missing values during early analysis | Validating dataset consistency before modeling | Created structured data preprocessing workflow
2 | Sprint 2 | 16-02-2026 | 2026-02-03 | Backend | Implement systematic feature engineering for demand patterns | Adding unnecessary features that increase complexity | Testing engineered features before model training | Finalized lag features and seasonality indicators
3 | Sprint 3 | 2026-02-03 | 16-03-2026 | AI Team | Apply hyperparameter tuning for machine learning models | Training models without performance comparison | Evaluating models using MAE and RMSE metrics | Selected best-performing forecasting model
4 | Sprint 4 | 16-03-2026 | 30-03-2026 | Backend + Frontend | Prepare forecasting outputs for capacity planning insights | Waiting until final stage for integration testing | Reviewing model predictions with visualization | Integrated forecasting results into planning workflow
5
6
7